## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-1 | Set up development tools and project workspace (JDK, IDE, GitHub) | MUST HAVE |  | Asifa Banu I | 3- Completed
Sprint 1 | Sprint 1 | US-2 | Create Product class and InventoryManager with OOP principles and error handling | MUST HAVE | US-1 | Asifa Banu I | 3- Completed
Sprint 1 | Sprint 1 | US-3 | Implement data storage using CSV files and manage version control with Git | MUST HAVE | US-1 | Asifa Banu I | 3- Completed
Sprint 1 | Sprint 1 | US-4 | Practice basic SQL and establish JDBC connection | MUST HAVE | US-1 | Asifa Banu I | 3- Completed
Sprint 2 | Sprint 2 | US-5 | Implement read operations (get all records, fetch by ID) and integrate with console menu | MUST HAVE | US-2, US-3, US-4 | Asifa Banu I | 3- Completed
Sprint 2 | Sprint 2 | US-6 | Add update and delete functionality for inventory records | MUST HAVE | US-5 | Asifa Banu I | 3- Completed
Sprint 2 | Sprint 2 | US-7 | Combine CRUD operations into console menu for end-to-end testing | MUST HAVE | US-5, US-6 | Asifa Banu I | 3- Completed
Sprint 2 | Sprint 2 | US-8 | Enhance input validation and handle runtime errors | MUST HAVE | US-7 | Asifa Banu I | 3- Completed
Sprint 2 | Sprint 2 | US-9 | Write unit tests using JUnit framework | MUST HAVE | US-7, US-8 | Asifa Banu I | 3- Completed
Sprint 3 | Sprint 3 | US10 | Develop CSVHelper utility to export inventory reports | MUST HAVE | US-3 | Asifa Banu I | 3- Completed
Sprint 3 | Sprint 3 | US-11 | Implement EmailService to send reports through SMTP | MUST HAVE | US-10 | Asifa Banu I | 3- Completed
Sprint 3 | Sprint 3 | US-12 | Add option in admin menu to generate reports | SHOULD HAVE | US-11 | Asifa Banu I | 3- Completed
Sprint 3 | Sprint 3 | US-13 | Integrate database, CSV export, and email service for complete reporting | MUST HAVE | US-10, US-11, US-12 | Asifa Banu I | 3- Completed
Sprint 3 | Sprint 3 | US-14 | Add OTP-based email verification during user registration | SHOULD HAVE | US-4 | Asifa Banu I | 3- Completed
Sprint 3 | Sprint 3 | US-15 | Provide menu options to verify email and resend OTP | COULD HAVE | US-14 | Asifa Banu I | 3- Completed
Sprint 4 | Sprint 4 | US-16 | Implement logic to monitor low-stock items | MUST HAVE | US-2, US-3 | Asifa Banu I | 3- Completed
Sprint 4 | Sprint 4 | US-17 | Develop scheduled task to automatically generate low-stock alerts | MUST HAVE | US-16 | Asifa Banu I | 3- Completed
Sprint 4 | Sprint 4 | US-18 | Enable email notifications for low-stock products | MUST HAVE | US-17, US-11 | Asifa Banu I | 3- Completed
Sprint 4 | Sprint 4 | US-19 | Package and deploy the full inventory management system | MUST HAVE | US-13, US-18 | Asifa Banu I | 3- Completed